## Sheet1
TODO List |  |  | KEY
Story | Estimation | Priority | Estimation | >0 | time (in hrs)
Make Sprites | 2 | 4 | Priority | 1 to 5 | 1 highest
Design a class to handle level generation | 5 | 1
Design a class to hold map | 4 | 1
Construct player controllers | 6 | 1
Build Enemy AI | 6 | 2
Iterate between levels | 1 | 3
Have a home UI | 1 | 5
Character/enemy interaction | 4 | 1
Item generation and abilites | 4 | 4
Add small story | 1 | 5
Leaderboard class | 6 | 4
Leaderboard UI | 2 | 4
Learn bluetooth | 6 | 3
Use bluetooth to allow multiplayer | 7 | 4
Total | 55